## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (or planned) | Date finished (or planned)
|  | This is an example. As a <> I want <> So that <> |  |  | This is an example. This is a new line 1. List 1 2. List 2 3. List 3
US-D01 | Data Storage | As a Developer, I want to implement a File I/O handler, so that all recruitment data is saved in .txt/csv files without using a database. | Must |  |  | 5 | Strictly follow the project's restriction that prohibits the use of the database.
US-D02 | Role Permission Control | As a Developer, I want to create a central authentication check, so that TA, MO and admin can only get access to their own functions (like only MO can delete jobs). | Must |  |  | 8 | Protect system security, ensure stable functions and safeguard personal privacy.
US-T01 | Main Workflow Test | As a Tester, I want to execute an end-to-end test from registration to job application, so that I can ensure the main workflow don't have any bug. | Should |  |  | 5 | The key step in verifying the stability of the system.
US-A01 | View Overall TA Workload | As an Administrator, I want to check the overall workload of all Teaching Assistants across different modules and activities, so that I can ensure a fair distribution of tasks and prevent overloading. |  |  |  |  | Core Requirement. The system must aggregate data from assigned jobs. Read/write operations must use simple text files (e.g., CSV, JSON), strictly adhering to the "no database" rule.
US-A02 | AI-Assisted Workload Balancing | As an Administrator, I want to receive AI-generated recommendations for balancing the workload among TAs, so that I can efficiently reassign tasks if someone is overbooked or underutilized. |  |  |  |  | AI Feature. AI outputs must not be blindly accepted; the system must provide explainable results and structured logic for its recommendations.
US-A03 | Monitor Global Recruitment Status | As an Administrator, I want to view a dashboard summarizing the global recruitment status (total jobs posted, applications pending, positions filled), so that I can track the overall progress of the TA recruitment for the semester. |  |  |  |  | Helps streamline the workflow from the previous Excel/forms process. Requires parsing and summarizing data from the plain text storage system.
US-A04 | Manage User Accounts | As an Administrator, I want to oversee and verify the registered accounts of Module Organisers and Teaching Assistants, so that I can maintain system security and ensure only authorized personnel use the application. |  |  |  |  | Essential for a complete prototype. Account statuses and roles must be managed and persisted within text files (e.g., XML or JSON).
US-A05 | Export Final Allocation Reports | As an Administrator, I want to export the finalized TA allocation and workload data into a standardized format, so that it can be shared with the school's HR or finance departments for payroll and record-keeping. |  |  |  |  | Ensures the system remains compatible with existing data and legacy systems. Output must be in a simple text format like CSV.
US-C01 | Overall Recruitment Monitoring | As a school administrator, I hope to monitor the recruitment progress of all subject modules on a dashboard, so that I can keep track of the vacancies in teaching positions. | Must |  |  | 8 | From a global management perspective, solve the problem of statistical opacity.
US-C02 | Application History Archive | As an HR professional, I would like to store and retrieve the past TA application data and feedback information in a simple text format, and also be able to preserve the records for a long time. | Should |  |  | 3 | Comply with the restrictions of "no use of database" and "data interoperability"
US-D03 | Concurrent File Writing Handle | As a Developer, I want to implement a file lock or queue mechanism, so that when multiple TAs apply for jobs at the exact same time, the local .txt/.csv data files are not corrupted or overwritten. | Must |  | 1. Simulate multiple users submitting data simultaneously. 2. The system accurately appends all records into the file without data loss. 3. The system does not crash or throw unhandled I/O exceptions during concurrent access. | 8 | Important for system stability since we can't use a standard database.
US-T02 | Invalid CV Upload Handle | As a Tester, I want to verify the system correctly blocks unsupported file types or oversized files when a TA uploads a CV, so that the application doesn't crash or store malicious files. | Should |  | 1. Uploading executable files (e.g., .exe, .sh) or files larger than 10MB must be rejected. 2. 2. A clear error message (e.g., "Invalid file format. Supported formats: PDF, DOC, DOCX, JPG, PNG") should be displayed on the UI. 3. Only standard document formats (.pdf, .docx) are saved to the local directory. | 3 | Addresses the edge case of user input error to safeguard personal privacy and system security.
US-MO01 | Post and Edit TA Job | As a Module Organiser, I want to create and update TA job posts, so that students can see accurate module details, requirements, deadlines, and vacancies. | must |  | 1. MO can create a TA job post. 2. MO can edit job details after posting. 3. Updated information is visible to applicants. |  | Essential MO-side function. Ensures vacancy information is clear, accurate, and can be updated when changes occur.
US-MO02 | View and Review Applicants | As a Module Organiser, I want to view applicant lists and their basic information, so that I can compare candidates more efficiently. | Must |  | 1. MO can open the applicant list for a job. 2. Applicant information is displayed clearly. 3. MO can review multiple applicants. |  | Helps the MO manage applications efficiently by displaying applicant details in a more organised way than forms or Excel files.
US-MO03 | Open CV and Assess Suitability | As a Module Organiser, I want to open and read applicants’ CVs, so that I can evaluate their skills, experience, and suitability for the role. | must |  | 1. MO can open an applicant’s CV. 2. CV content is displayed correctly. 3. MO can use the CV to support decision-making. |  | Supports fairer selection by allowing the MO to check applicants’ background, skills, and relevant experience.
US-MO04 | Update Applicant Status and Final Result | As a Module Organiser, I want to mark applicants as under review, accepted, or rejected and record the final recruitment result, so that the hiring process is clear and organised. | must |  | 1. MO can assign a status to each applicant. 2. Final result can be recorded. 3. Job status updates after recruitment is completed |  | Keeps the recruitment workflow structured and makes final decisions easier to record and track.
US-MO05 | Monitor Recruitment Progress | As a Module Organiser, I want to track the number of applicants, confirmed hires, and remaining vacancies in real time, so that I can manage recruitment progress more effectively. | should |  | 1. System shows total applicants. 2. System shows confirmed hires. 3. System shows remaining vacancies. |  | Improves transparency by showing applicant numbers, confirmed hires, and remaining vacancies in real time.
US-TA01 | Create Applicant Profile | As a TA applicant, I want to create my profile with my student ID, programme, year of study and contact details, so that I can use this information for future job applications. | must |  |  |  | Basic personal information for later applications.
US-TA02 | Upload CV | As a TA applicant, I want to upload and update my CV, so that I can use the latest version when applying for TA positions. | must |  |  |  | CV upload before applying.
US-TA03 | View Available Jobs | As a TA applicant, I want to view current TA vacancies with the module name, requirements and deadline, so that I can identify suitable positions and prepare my application. | must |  |  |  | Job list with basic information.
US-TA04 | Apply for a Job | As a TA applicant, I want to apply for a TA position using my saved profile and CV, so that I can submit my application efficiently. | must |  |  |  | Link application with profile and CV.
US-TA05 | Check Application Status | As a TA applicant, I want to check the status of my submitted applications, so that I can see whether they have been received, are under review, or have a final result. | must |  |  |  | Status tracking page.
US-T04 | Form Input Validation Test | As a Tester, I want to verify that all user input forms (job posting, application submission, profile creation) correctly validate required fields and data formats, so that invalid or incomplete data is rejected before being saved to files. | should |  |  |  | Ensures data integrity.
US-A06 | User Account Management (Registration, Login, Password Recovery) | As an Administrator, I want to provide a secure account registration and login system for TAs and MOs, with password recovery functionality, so that all users can safely access the system and recover their accounts if they forget their credentials. | must |  |  |  | A foundational requirement for the entire system.