## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (or planned) | Date finished (or planned)
|  | This is an example. As a <> I want <> So that <> |  |  | This is an example. This is a new line 1. List 1 2. List 2 3. List 3
US-D01 | Data Storage | As a Developer, I want to implement a File I/O handler, so that all recruitment data is saved in .txt/csv files without using a database. | Must | 1 | 1. Users must log in, and their sessions strictly reflect their assigned roles (TA, MO, or Admin). 2. A TA attempting to access MO-specific functions (e.g., "Post Jobs") or Admin functions is blocked and shown an "Access Denied" error message. 3. Unauthenticated users are automatically redirected to the login page when trying to access any internal system URLs. | 5 | Strictly follow the project's restriction that prohibits the use of the database. | 3/23 | 3/30
US-D02 | Role Permission Control | As a Developer, I want to create a central authentication check, so that TA, MO and admin can only get access to their own functions (like only MO can delete jobs). | Must | 1 | 1. Users must log in, and their sessions strictly reflect their assigned roles (TA, MO, or Admin). 2. A TA attempting to access MO-specific functions (e.g., "Post Jobs") or Admin functions is blocked and shown an "Access Denied" error message. 3. Unauthenticated users are automatically redirected to the login page when trying to access any internal system URLs. | 5 | Protect system security, ensure stable functions and safeguard personal privacy. | 3/23 | 3/30
US-T01 | Main Workflow Test | As a Tester, I want to execute an end-to-end test from registration to job application, so that I can ensure the main workflow don't have any bug. | Should | 2 | 1. The test successfully simulates a complete flow: TA registers, uploads a CV, applies for a job, and the MO approves the application. 2. The system does not crash or freeze at any point during this end-to-end process. 3. All status changes generated during the test are correctly verified and recorded in the underlying .txt/.csv files. | 3 | The key step in verifying the stability of the system. | 3/31 | 4/12
US-A01 | View Overall TA Workload | As an Administrator, I want to check the overall workload of all Teaching Assistants across different modules and activities, so that I can ensure a fair distribution of tasks and prevent overloading. | Should | 3 | 1. The Admin dashboard accurately calculates and displays the total working hours or task count for each TA. 2. The system correctly aggregates workload data by reading from multiple module assignment text files. 3. TAs who exceed a predefined maximum workload threshold are visually highlighted (e.g., marked in red) to prevent overloading. | 3 | Core Requirement. The system must aggregate data from assigned jobs. Read/write operations must use simple text files (e.g., CSV, JSON), strictly adhering to the "no database" rule. | 4/13 | 4/28
US-A02 | AI-Assisted Workload Balancing | As an Administrator, I want to receive AI-generated recommendations for balancing the workload among TAs, so that I can efficiently reassign tasks if someone is overbooked or underutilized. | Could | 4 | 1. The system successfully analyzes current TA workloads and generates recommendations for task reassignment. 2. AI-generated outputs are not blindly executed; they provide structured logic and explainable reasons for each recommendation. 3. The Admin retains final approval rights; the system requires human confirmation before applying the AI's reassignments. | 8 | AI Feature. AI outputs must not be blindly accepted; the system must provide explainable results and structured logic for its recommendations. | 4/29 | 5/10
US-A03 | Monitor Global Recruitment Status | As an Administrator, I want to view a dashboard summarizing the global recruitment status (total jobs posted, applications pending, positions filled), so that I can track the overall progress of the TA recruitment for the semester. | Should | 3 | 1. The dashboard accurately displays aggregated statistics: total jobs posted, pending applications, and positions filled. 2. The statistics update dynamically or upon page refresh when a new application is submitted or a status is changed. 3. Data is efficiently parsed from the text-based storage without causing severe UI lagging. | 3 | Helps streamline the workflow from the previous Excel/forms process. Requires parsing and summarizing data from the plain text storage system. | 4/13 | 4/28
US-A04 | Manage User Accounts | As an Administrator, I want to oversee and verify the registered accounts of Module Organisers and Teaching Assistants, so that I can maintain system security and ensure only authorized personnel use the application. | Must | 3 | 1. The Admin can view a complete list of all registered TAs and MOs in the system. 2. The Admin can manually approve, suspend, or delete user accounts, and these changes are instantly saved to the text files. 3. Suspended or deleted users are immediately prevented from logging into the application. | 3 | Essential for a complete prototype. Account statuses and roles must be managed and persisted within text files (e.g., XML or JSON). | 4/13 | 4/28
US-A05 | Export Final Allocation Reports | As an Administrator, I want to export the finalized TA allocation and workload data into a standardized format, so that it can be shared with the school's HR or finance departments for payroll and record-keeping. | Could | 3 | 1. The Admin can click an "Export" button to generate a standardized file (e.g., .csv) of all finalized TA allocations. 2. The exported report includes essential payroll fields: TA Name, Module Assigned, and Total Hours. 3. The exported file is formatted correctly and can be opened by standard spreadsheet software (like MS Excel) without data corruption. | 2 | Ensures the system remains compatible with existing data and legacy systems. Output must be in a simple text format like CSV. | 4/13 | 4/28
US-C01 | Overall Recruitment Monitoring | As a school head,I hope to deploy a system that does not require database configuration and has very little server maintenance, so that we can reduce the financial cost and technical barrier of the project. | Must | 1 | 1. The system can be successfully deployed and started without requiring any external database configuration (e.g., no MySQL or MongoDB installation). 2. All system data persistence relies entirely on local, lightweight plain text files (e.g., .txt, .csv, .json). 3. The deployment guide in the README file clearly demonstrates that starting the application involves minimal server maintenance and zero database setup. | 5 | From a global management perspective, solve the problem of statistical opacity. | 3/23 | 3/30
US-C02 | Application History Archive | As the administrative supervisor, I would like to obtain the standard plain text versions of all TA application histories, so as to keep offline records for auditing purposes and be able to easily share the data with other departments. | Could | 2 | 1. The administrative supervisor can click a single button to export the complete TA application history from the system. 2. The exported archive is strictly in a standard, human-readable plain text format (e.g., .csv or .txt) that can be easily opened without specialized software. 3. The exported offline records accurately contain all necessary data fields (applicant details, roles, feedback) required for auditing by other departments. | 2 | Comply with the restrictions of "no use of database" and "data interoperability" | 3/31 | 4/12
US-D03 | Concurrent File Writing Handle | As a Developer, I want to implement a file lock or queue mechanism, so that when multiple TAs apply for jobs at the exact same time, the local .txt/.csv data files are not corrupted or overwritten. | Must | 4 | 1. Simulate multiple users submitting data simultaneously. 2. The system accurately appends all records into the file without data loss. 3. The system does not crash or throw unhandled I/O exceptions during concurrent access. | 8 | Important for system stability since we can't use a standard database. | 4/29 | 5/10
US-T02 | Invalid CV Upload Handle | As a Tester, I want to verify the system correctly blocks unsupported file types or oversized files when a TA uploads a CV, so that the application doesn't crash or store malicious files. | Should | 4 | 1. Uploading executable files (e.g., .exe, .sh) or files larger than 10MB must be rejected. 2. 2. A clear error message (e.g., "Invalid file format. Supported formats: PDF, DOC, DOCX, JPG, PNG") should be displayed on the UI. 3. Only standard document formats (.pdf, .docx) are saved to the local directory. | 3 | Addresses the edge case of user input error to safeguard personal privacy and system security. | 4/29 | 5/10
US-MO01 | Post and Edit TA Job | As a Module Organiser, I want to create and update TA job posts, so that students can see accurate module details, requirements, deadlines, and vacancies. | Must | 2 | 1. MO can create a TA job post. 2. MO can edit job details after posting. 3. Updated information is visible to applicants. | 3 | Essential MO-side function. Ensures vacancy information is clear, accurate, and can be updated when changes occur. | 3/31 | 4/12
US-MO02 | View and Review Applicants | As a Module Organiser, I want to view applicant lists and their basic information, so that I can compare candidates more efficiently. | Must | 2 | 1. MO can open the applicant list for a job. 2. Applicant information is displayed clearly. 3. MO can review multiple applicants. | 3 | Helps the MO manage applications efficiently by displaying applicant details in a more organised way than forms or Excel files. | 3/31 | 4/12
US-MO03 | Open CV and Assess Suitability | As a Module Organiser, I want to open and read applicants’ CVs, so that I can evaluate their skills, experience, and suitability for the role. | Must | 1 | 1. MO can open an applicant’s CV. 2. CV content is displayed correctly. 3. MO can use the CV to support decision-making. | 2 | Supports fairer selection by allowing the MO to check applicants’ background, skills, and relevant experience. | 3/23 | 3/30
US-MO04 | Update Applicant Status and Final Result | As a Module Organiser, I want to mark applicants as under review, accepted, or rejected and record the final recruitment result, so that the hiring process is clear and organised. | Must | 2 | 1. MO can assign a status to each applicant. 2. Final result can be recorded. 3. Job status updates after recruitment is completed | 2 | Keeps the recruitment workflow structured and makes final decisions easier to record and track. | 3/31 | 4/12
US-MO05 | Monitor Recruitment Progress | As a Module Organiser, I want to track the number of applicants, confirmed hires, and remaining vacancies in real time, so that I can manage recruitment progress more effectively. | Should | 3 | 1. System shows total applicants. 2. System shows confirmed hires. 3. System shows remaining vacancies. | 3 | Improves transparency by showing applicant numbers, confirmed hires, and remaining vacancies in real time. | 4/13 | 4/28
US-TA01 | Create Applicant Profile | As a TA applicant, I want to create my profile with my student ID, programme, year of study and contact details, so that I can use this information for future job applications. | Must | 2 | 1. The TA can input profile details (student ID, programme, year of study, contact info) and save them successfully. 2. The profile data is securely stored in a designated user profile text file (.json or .csv). 3. Upon returning to the profile page, the TA sees their previously saved details accurately loaded from the local file. | 3 | Basic personal information for later applications. | 3/31 | 4/12
US-TA02 | Upload CV | As a TA applicant, I want to upload and update my CV, so that I can use the latest version when applying for TA positions. | Must | 2 | 1. The TA can browse their local device and select a CV file to upload to the system. 2. The file is saved to a specific local directory, and its relative path is linked to the TA's profile in the text database. 3. Uploading a new CV successfully overwrites or updates the path to the previous one, ensuring the MO always sees the latest version. | 3 | CV upload before applying. | 3/31 | 4/12
US-TA03 | View Available Jobs | As a TA applicant, I want to view current TA vacancies with the module name, requirements and deadline, so that I can identify suitable positions and prepare my application. | Must | 1 | 1. The TA can view a comprehensive list of all active TA job postings available in the system. 2. The system correctly filters out and hides jobs whose application deadlines have already passed. 3. All displayed job details exactly match the information stored in the job postings text file. | 2 | Job list with basic information. | 3/23 | 3/30
US-TA04 | Apply for a Job | As a TA applicant, I want to apply for a TA position using my saved profile and CV, so that I can submit my application efficiently. | Must | 2 | 1. The TA can apply for a specific job with a single click, using their pre-saved profile and uploaded CV. 2. The application record (linking the TA's ID and the Job ID) is successfully appended to the applications .txt or .csv file. 3. The system prevents the TA from applying for the exact same job twice. | 3 | Link application with profile and CV. | 3/31 | 4/12
US-TA05 | Check Application Status | As a TA applicant, I want to check the status of my submitted applications, so that I can see whether they have been received, are under review, or have a final result. | Should | 2 | 1. The TA can view a dedicated page listing all the TA positions they have applied for. 2. The current status (e.g., "Received", "Under Review", "Accepted", "Rejected") is clearly displayed next to each application. 3. The displayed status perfectly matches the updates made by the MO in the underlying data files. | 2 | Status tracking page. | 3/31 | 4/12
US-T04 | Form Input Validation Test | As a Tester, I want to verify that all user input forms (job posting, application submission, profile creation) correctly validate required fields and data formats, so that invalid or incomplete data is rejected before being saved to files. | Must | 1 | 1. Submitting a form with missing mandatory fields triggers a specific validation error message on the UI. 2. Inputting invalid data formats (e.g., entering letters in a phone number field) is instantly rejected by the system. 3. No invalid or incomplete data records are allowed to be written into the .txt/.csv storage files. | 3 | Ensures data integrity. | 3/23 | 3/30
US-A06 | User Account Management (Registration, Login, Password Recovery) | As an Administrator, I want to provide a secure account registration and login system for TAs and MOs, with password recovery functionality, so that all users can safely access the system and recover their accounts if they forget their credentials. | Must | 1 | 1. Users can securely register and log in, with their credentials verified against a central user accounts text file. 2. Passwords are not stored in plain text (e.g., they must be hashed) within the local file to ensure basic security. 3. Users can successfully reset their passwords (e.g., via security questions), and the new credentials update correctly in the text file. | 5 | A foundational requirement for the entire system. | 3/23